## Estimation
MC Holdings Inc. Group
WBS of Image-2-Slides - Version 1
Updated: 2019/02/28
Task |  | Sub-Task Level 1 | Sub-Task Level 2 | Effort (Man-Days) | Start date | End date | Progress (%) | March |  |  |  | April |  |  |  |  | May |  |  |  |  | June |  |  |  |  | July |  |  |  |  | August |  |  |  |  | September | [5 empty] | October |  |  |  |  | November
[8 empty] | 1 (03/04 - 03/10) | 2 (03/11 - 03/17) | 3 (03/18 - 03/24) | 4 (03/25 - 03/31) | 5 (04/01 - 04/07) | 6 (04/08 - 04/14) | 7 (04/15 - 04/21) | 8 (04/22 - 04/28) | 9 (04/29 - 05/05) |  | 10 (06/05 - 12/05) | 11 (13/05 - 19/05) | 12 (20/05 - 26/05) | 13 (27/05 - 02/06) |  | 14 (03/06 - 09/06) | 15 (10/06 - 16/06) | 16 (17/06 - 23/06) | 17 (24/06 - 30/06) | 18 (01/07 - 07/07) | 19 (08/07 - 14/07) | 20 (15/07 - 21/07) | 21 (22/07 - 28/07) | 22 (29/07 - 04/08) |  | 23 (05/08 - 11/08) | 24 (12/08 - 18/08) | 25 (19/08 - 25/08) | 26 (26/08 - 01/09) |  | 27 (02/09 - 08/09) | 28 (09/09 - 15/09) | 29 (16/09 - 22/09) | 30 (23/09 - 29/09) | 31 (30/09 - 06/10) |  | 32 (07/10 - 13/10) | 33 (14/10 - 20/10) | 34 (21/10 - 27/10) | 35 (28/10 - 03/11) |  | 36 (04/11 - 10/11)
AI Modules Development
| Pre-processing |  |  | 10 |  |  | 0
| Object Recognition | Text Recognition | Investigating Existing Deep Learning Solutions | 0 |  |  | 0
|  |  | Applying to recognize English | 0 |  |  | 0
|  |  | Applying to recognize Japanese | 0 |  |  | 0
|  | Line Detection | Pre-processing | 4.5 |  |  | 0
|  |  | Implement solutions | 8 |  |  | 0
|  |  | Post-processing | 6 |  |  | 0
|  | Polygons Detection | Data Creating | 20 |  |  | 0
|  |  | Model Design | 7 |  |  | 0
|  |  | Model Implementing | 5 |  |  | 0
|  |  | Training and Tuning | 20 |  |  | 0
|  | Marks Detection | Data Creating | 0 |  |  | 0
|  |  | Model Design | 0 |  |  | 0
|  |  | Model Implementing | 0 |  |  | 0
|  |  | Training and Tuning | 0 |  |  | 0
|  | Objects Classification | Data Creating | 20 |  |  | 0
|  |  | Model Design | 7 |  |  | 0
|  |  | Model Implementing | 5 |  |  | 0
|  |  | Training and Tuning | 20 |  |  | 0
| Layout Generation | Layout Generation | Investigate PPTX generation library | 8 |  |  | 0
|  |  | Design solution making | 10 |  |  | 0
|  | PPTX Generation | Implementation | 10 |  |  | 0
| BrSE |  |  | 80.25 |  |  | 0
Demo Development
| Requirement Analysis |  |  | 0 |  |  | 0
| AI Module Integration | Module Integration |  | 0 |  |  | 0
|  | GUI |  | 0 |  |  | 0
| Simple Testing |  |  | 0 |  |  | 0
| Create Technical Report & Guideline |  |  | 0 |  |  | 0
|  |  | Total (man-days) | 240.75
|  |  | Total (man-months) | 12.0375
|  |  | Discount | 3.0375
|  |  | Total Effort of AI Core Tasks (man-months) | 2.7
|  |  | Total Effort of Non AI Core Tasks (man-months) | 9.3375
Scope of Version 1
| Text Recognition | No
| Line Recognition | Straight Line only
| Polygon Recognition | Triangle, Rectangle, Circle
| Mark Recognition | No
| PPTX Generation | Yes
Deliverables
| Source code | Yes
| Data | Yes
| Report & Guideline | Yes